## Deal tasks
Tasks & Milestones
Deal SetupWed May 26
Confirm Buyer's Legal Name(s) & Add to Deal RoomSteve Novak completedWed, May 26
Add Milestone Dates & Relevant Notes to Deal RoomSteve Novak completedWed, May 26
Verify Commission Amount & MLS Fee and Add to Deal RoomSteve Novak completedWed, May 26
Upload Fully Executed Documents to Deal RoomSteve Novak completedWed, May 26
Send "Ready to Go" Email to TC once all Information has been Added to Deal RoomSteve Novak completedWed, May 26
Verify Milestone DatesJessica Santana completedWed, May 26
Wed, May 26 at 12:50pm · Jessica Santana
al correct
Verify NET or GROSS, ensure refund box is correct & make note on invoice taskJessica Santana completedWed, May 26
Wed, May 26 at 12:51pm · Jessica Santana
2.5% commission based on gross sale price
Upload MLS SheetJessica Santana completedWed, May 26
Wed, May 26 at 12:51pm · Jessica Santana
uploaded
Create Linked Account for Co-Buyer (if needed)Jessica Santana completedWed, May 26
Wed, May 26 at 12:51pm · Jessica Santana
Steve created
Audit Opening Documents and Deal Room, Send Audit Recap/Needs to Agent and cc TM and SMJessica Santana completedWed, May 26
Publish Deal Room to CustomerJessica Santana completedWed, May 26
Wed, May 26 at 12:52pm · Jessica Santana
published
Mutual AcceptanceWed May 26
Send Welcome Letter to BuyerJessica Santana completedWed, May 26
Make Introduction/Welcome Call to BuyerJessica Santana completedWed, May 26
Wed, May 26 at 12:55pm · Jessica Santana
Called and spoke to Jessica.
Send Welcome Letter to Listing AgentJessica Santana completedWed, May 26
Confirm or add property unit number, if applicableJessica Santana completedWed, May 26
Wed, May 26 at 1:05pm · Jessica Santana
added
Choose Inspector and Schedule Home InspectionJessica Santana completedWed, May 26
Add Listing Agent's Staff to Deal RoomJessica Santana completedWed, May 26
Wed, May 26 at 1:05pm · Jessica Santana
added
Add Seller's Attorney & Staff to Deal RoomJessica Santana completedFri, May 28
Fri, May 28 at 12:29pm · Jessica Santana
added
Choose LenderJessica Ferguson completedThu, May 27
Thu, May 27 at 5:56pm · Jessica Ferguson
Working with Carrie Carrizosa at Leader Bank.
Choose an AttorneyJessica Ferguson completedSat, May 29
Sat, May 29 at 3:43pm · Jessica Ferguson
Sarah Ricciardelli
Add Buyer's Attorney & Staff to Deal Room (mark as Buyer Attorney & Title)Jessica Santana completedTue, Jun 1
Fri, May 28 at 9:35am · Jessica Santana
requested
Tue, Jun 1 at 9:37am · Jessica Santana
added
Send Intro Letter to Buyer's Attorney w/ offer/MLS SheetJessica Santana completedTue, Jun 1
Send Buyer's Attorney Info to Listing Agent (If Wasn't Sent in Welcome Letter)Jessica Santana completedTue, Jun 1
Tue, Jun 1 at 10:03am · Jessica Santana
sent in connecting attorneys email
Send Intro Email connecting Attorneys & Agents (Buyer's & Seller's)Jessica Santana completedTue, Jun 1
Confirm Buyer's Final Lender Choice (Update Agent Tools if Needed)Jessica Santana completedFri, May 28
Fri, May 28 at 9:33am · Jessica Santana
confirmed
Add Lender & Staff to Deal RoomJessica Santana completedFri, May 28
Fri, May 28 at 9:34am · Jessica Santana
added
Send Welcome Letter to Lender (Attach Fully Executed Contract & Earnest Money Check)Jessica Santana completedWed, Jun 2
Send Lender Info to Listing Agent (if wasn't sent in Welcome Letter)Jessica Santana completedWed, Jun 2
Wed, Jun 2 at 10:40am · Jessica Santana
sent
Earnest MoneyWed May 26
Verify with Buyer that Deposit is in TransitJessica Santana completedWed, May 26
Wed, May 26 at 1:06pm · Jessica Santana
depositlink
Schedule Agent/AA or send mailing label for Earnest Money Check pickup/deliveryJessica Santana completedWed, May 26
Wed, May 26 at 2:36pm · Jessica Santana
deposit link
Ensure copy of Earnest Money check in file (ask buyer or listing agent if not received)Jessica Santana completedWed, May 26
Wed, May 26 at 1:05pm · Jessica Santana
in file
Follow-up to ensure Earnest Money Received by listing agentJessica Santana completedFri, May 28
Fri, May 28 at 11:32am · Jessica Santana
sent email
Fri, May 28 at 12:29pm · Jessica Santana
received
Ensure lender has copy of EM check, if not sent with welcome emailJessica Santana completedWed, Jun 2
Wed, Jun 2 at 10:38am · Jessica Santana
sent
InspectionTue Jun 1
Add Inspector(s) & Staff Contact Info to Deal RoomJessica Santana completedThu, May 27
Thu, May 27 at 7:13am · Jessica Santana
chosen, not provided
Confirm Buyer has Scheduled Home Inspection(s) - Get Tentative Date/TimeJessica Santana completedThu, May 27
Thu, May 27 at 7:44am · Jessica Santana
confirmed
Confirm Inspection Appointment with BuyerJessica Santana completedThu, May 27
Thu, May 27 at 7:44am · Jessica Santana
confirmed
Notify Listing Agent of Inspection Appointment - Confirm Property Access and Utilities On for InspectionJessica Santana completedThu, May 27
Thu, May 27 at 7:44am · Jessica Santana
notified
Schedule Agent or AA for Inspection in Agent Tools (if AA, schedule Agent for Drop-in)Jessica Santana completedThu, May 27
Thu, May 27 at 7:45am · Jessica Santana
schedued Steve
Change Deal Stage to STI (Once Inspection is Scheduled)Jessica Santana completedThu, May 27
Thu, May 27 at 7:45am · Jessica Santana
changed
Review Inspection Report Received from InspectorJessica Santana completedTue, Jun 1
Review Inspection Report with BuyerJessica Santana completedTue, Jun 1
Negotiate Repairs or Credit based upon Inspection Results (if applicable)Jessica Santana completedTue, Jun 1
Negotiate Extension for Inspection Contingency (if needed)Jessica Santana completedTue, Jun 1
Follow up with Agent on Inspection Negotiation Status, Create Extension Addendum If NeededJessica Santana completedWed, Jun 2
Wed, Jun 2 at 10:40am · Jessica Santana
in process
Coordinate & Schedule Buyer's Follow-Up Inspections with Listing Agent, Add to Agent ToolsJessica Santana completedWed, Jun 2
Wed, Jun 2 at 10:41am · Jessica Santana
no follow ups
Confirm if Inspector Left Radon KitJessica Santana completedWed, Jun 2
Wed, Jun 2 at 10:40am · Jessica Santana
no raodn
Follow up with Buyer & Agent on any Specialized Inspections Needed/DesiredJessica Santana completedWed, Jun 2
Wed, Jun 2 at 10:41am · Jessica Santana
none needed
Purchase & Sale DepositFri Jun 4
Confirm with attorney/listing agent who the P&S check should made out to and confirm delivery addressJessica Santana completedWed, Jun 2
Wed, Jun 2 at 10:40am · Jessica Santana
sent email
Wed, Jun 2 at 11:58am · Jessica Santana
Depositlink
Send P&S milestone & check reminder to buyerJessica Santana completedWed, Jun 2
Wed, Jun 2 at 11:58am · Jessica Santana
Depositlink
Verify with Buyer that Secondary Deposit is in transitJessica Santana completedFri, Jun 4
Fri, Jun 4 at 3:47pm · Jessica Santana
deposit made
Schedule Agent/AA or send mailing label for Secondary deposit pickup/delivery OR send mailing labelJessica Santana completedFri, Jun 4
Fri, Jun 4 at 3:48pm · Jessica Santana
depositlink
Deliver Secondary deposit to listing agent or his/her officeJessica Santana completedFri, Jun 4
Fri, Jun 4 at 3:48pm · Jessica Santana
deposit made
Ensure copy of Earnest Money check in file (ask buyer or listing agent if not received)Jessica Santana completedFri, Jun 4
Fri, Jun 4 at 3:48pm · Jessica Santana
in file
Verify Secondary/Increased Deposit receivedJessica Santana completedMon, Jun 7
Mon, Jun 7 at 9:02am · Jessica Santana
sent email
Mon, Jun 7 at 10:07am · Jessica Santana
received
Email Secondary Earnest Money Receipt/Check Copy to LenderJessica Santana completedMon, Jun 7
Mon, Jun 7 at 9:01am · Jessica Santana
sent
Purchase & Sale AgreementFri Jun 4
Follow up with Buyer's Attorney on Purchase & Sale Draft StatusJessica Santana completedThu, Jun 3
Review & Sign Purchase & Sale AgreementJessica Santana completedFri, Jun 4
Fri, Jun 4 at 3:48pm · Jessica Santana
signed
Send Purchase & Sale Agreement to Buyer for SignatureJessica Santana completedFri, Jun 4
Fri, Jun 4 at 2:52pm · Jessica Santana
sent
Audit Deal & Milestone Dates Based on P&S - confirm with agent/attorney if there are discrepancies.Jessica Santana completedFri, Jun 4
Fri, Jun 4 at 2:52pm · Jessica Santana
looks good
Send Redfin Refund Letter to LenderJessica Santana completedMon, Jun 7
Send Executed Purchase & Sale minus Repair Rider to Lender (cc Buyer)Jessica Santana completedMon, Jun 7
Mon, Jun 7 at 9:01am · Jessica Santana
sent
Send Executed Purchase & Sale plus Repair Rider to Buyer's Attorney (cc Buyer)Jessica Santana completedMon, Jun 7
Mon, Jun 7 at 9:02am · Jessica Santana
sent
Change Stage to Pending (When All Contingencies Removed)Jessica Santana completedMon, Jun 7
Mon, Jun 7 at 9:02am · Jessica Santana
changed
Send what to expect after the P&S email to buyerJessica Santana completedMon, Jun 7
Ensure Buyers are Working on Homeowner's InsuranceJessica Santana completedWed, Jun 9
Order Homeowner's InsuranceJessica Santana completedWed, Jun 9
Order and Pay for Appraisal (with Lender)Jessica Santana completedWed, Jun 9
Wed, Jun 9 at 11:19am · Jessica Santana
ordered
Confirm with buyer appraisal has been orderedJessica Santana completedWed, Jun 9
Wed, Jun 9 at 10:37am · Jessica Santana
sent email
Wed, Jun 9 at 11:19am · Jessica Santana
ordered
HOA DocumentsFri Jun 4
Follow-up with listing agent for HOA docs, if not received yetJessica Santana completedFri, May 28
Fri, May 28 at 11:31am · Jessica Santana
in file
Email HOA docs to buyer and buyer attorney for reviewJessica Santana completedTue, Jun 1
Tue, Jun 1 at 10:06am · Jessica Santana
sent
Review HOA DocsJessica Santana completedWed, Jun 2
FinancingFri Jun 25
Confirm Closing Attorney (Buyer's Attorney or Newly Designated), Add to Deal Room if Newly DesignatedJessica Santana completedTue, Jun 15
Tue, Jun 15 at 3:18pm · Jessica Santana
Sarah Ricciardelli
Follow up with Lender on Loan ProgressJessica SantanaFri, Jun 18
Send Commitment Reminder to LenderJessica SantanaFri, Jun 25
Review Financing Commitment/Approval LetterBuyerFri, Jun 25
ClosingFri Jul 9
Prepare Commission Invoice (verify Net or Gross), Send to Listing Agent & Closing Company and request a list of utilities from the sellers to pass along to the buyersJessica SantanaFri, Jun 25
Send Pre-Close Letter to Buyer (Include Utilities List)Jessica SantanaFri, Jun 25
Follow-up & Add to Deal Room & Refund Dialog Buyer Mailing Address Post-CloseJessica SantanaTue, Jun 29
Confirm Utility Providers with Listing Agent, if not receivedJessica SantanaThu, Jul 1
Remind Buyer to transfer UtilitiesJessica SantanaFri, Jul 2
Transfer Utilities (Effective for Date of Possession)BuyerFri, Jul 2
Confirm with Lender we have the Clear to CloseJessica SantanaMon, Jul 5
Update Buyer's Attorney on Clear to Close StatusJessica SantanaMon, Jul 5
Schedule Closing with Closing Attorney's OfficeBuyerMon, Jul 5
Confirm Key Exchange Method with Listing AgentJessica SantanaMon, Jul 5
Follow up with Buyer and Input How They Heard about Redfin (if info is missing)Jessica SantanaMon, Jul 5
Rate Listing Agent: Would this Agent be a Good Fit for Redfin?Steve NovakMon, Jul 5
Ensure attorney has send CD to buyer for review and request copy to review commission amountsJessica SantanaTue, Jul 6
Review Estimated Closing Disclosure/StatementBuyerTue, Jul 6
Review Estimated Closing Disclosure/Statement (Agent)Steve NovakTue, Jul 6
Verify Buyer Name on Closing Statement Matches Refund InstructionsJessica SantanaTue, Jul 6
Confirm Buyer's Closing/Signing Appointment with buyer/closing attorneyJessica SantanaTue, Jul 6
Check-in w/ Agent - should we schedule Agent or AA to Attend ClosingJessica SantanaTue, Jul 6
Check-in with escrow agent: who will be cutting Redfin's check & will it be at closingJessica SantanaThu, Jul 8
Verify Commission Instructions/Statement amounts and Confirm Seattle addressJessica SantanaThu, Jul 8
Confirm RecordingJessica SantanaFri, Jul 9
Congratulate Buyer (from Agent)Steve NovakFri, Jul 9
Ask Buyer for Referral (Friends/Family)Steve NovakFri, Jul 9
Send Congrats Email to Buyer (from TC)Jessica SantanaFri, Jul 9
Add Any Commission Adjustments to Agent Tools, Upload Applicable Approval Letters and NotesJessica SantanaFri, Jul 9
Confirm Sales Price & Commission to Match Final Closing Statement & Deal RoomJessica SantanaFri, Jul 9
Upload Fully Executed Buyer/Combined Settlement StatementJessica SantanaFri, Jul 9
Change Deal Stage to Closed or Closed - Docs Incomplete (if you don't have all documents)Jessica SantanaFri, Jul 9
Confirm MLS Changed to Closed with Correct Agent InfoJessica SantanaFri, Jul 9
Prepare USPS Label to for Settlement Statement/Commission Check (if needed)Jessica SantanaFri, Jul 9
Rate Your Service ProvidersBuyerSat, Jul 10
Return Redfin SurveyBuyerSat, Jul 10
Complete/Verify All Documents Uploaded to Agent ToolsJessica SantanaMon, Jul 12
Mail Closing Statement & Commission Check to Accounting (if applicable)Jessica SantanaMon, Jul 12
Final WalkthroughFri Jul 9
Check Buyer Availability for Final WalkthroughJessica SantanaTue, Jul 6
Confirm Final Walkthrough Date/Time and Access with Listing Agent, Re-Confirm Date/Time with BuyerJessica SantanaWed, Jul 7
Schedule Walkthrough Appointment in Agent ToolsJessica SantanaWed, Jul 7
Send Repair Invoices to Buyer & Agent/AA Attending WalkthroughJessica SantanaThu, Jul 8
Complete or Waive Final WalkthroughSteve NovakFri, Jul 9
Documents
Add Post-Mutual Document
Upload
Hide WaivedHide Final Documents
Sort byNameStatusMost RecentNameUpdated By
Required (15 of 18)
Other (8)
Photos (0)
Affiliated Business DisclosureAffiliated_Business_Arrangement_Disclosure.pdfFinal
Closing Disclosure/ALTANot yet uploaded
Commission Check (required after close)Not yet uploaded
Commission InvoiceNot yet uploaded
Copy Of Offer CheckDeposit Link Confirmation.pdfFinal
Copy Of P&S CheckScreenshot 2021-06-04 3.43.05 PM.pngFinal
GBREB Buyer Representation AgreementFergusonCondoQuestionnaire_20210609.pdfFinal
Home Inspectors - Facts For ConsumersHome_Inspectors_-_Facts_for_Consumers.pdfFinal
MLS Sheet1460 Cambridge St MLS.pdfFinal
Mandatory MA Agency DisclosureMandatory_MA_Agency_Disclosure.pdfFinal
Offer - Fully SignedFE_Offer_1460_Cambridge_St_Unit_5_.pdfFinal
Preapproval/Proof Of FundsPreapproval_Proof_Of_Funds.pdfFinal
Purchase & Sale AgreementFergusonPS (1).pdfFinal
Redfin Buyer Representation AgreementRedfin_Buyer_Representation_Agreement.pdfFinal
Show Less
You can add documents via email